## Instructions
Weed Management Plan
Instructions
Updated: 7/2001
This worksheet is designed to accompany the Weed Management Template, available at the Wildland Invasive Species Program web site (url below).
The worksheet consists of five tables. Cells in the tables are color coded.
You should enter data into cells that are shaded yellow, like this cell, since they are used in computations elsewhere in the workbook.
Cells shaded purple, like this one, are calculated by the workbook. You should not have to enter data into these cells.
Cells without any shading (i.e. white) do not need data entered into them.
You will find it easiest to proceed by entering data first into Table 1, then Table 2, etc. Table 5 is self-completing.
This worksheet can easily be expanded to handle more than 12 weeds, or to compute for more than 1 year of management work at a time. If you need such a worksheet, but do not know how to create it yourself, contact the Wildland Invasive Species Program staff for cheery assistance.
Contact information:
Wildland Invasive Species Program
The Nature Conservancy
http://tncweeds.ucdavis.edu

## Table 1--Priorities
Weed Management Plan
Table 1. Prioritized List of Weed Species
Updated: 7/2001
Note: Yellow fields must be completed--they are used elsewhere in this workbook.
-- Rank/Priority --
Scientific Name | Common Name | Riparian | Wetland | Grassland | Trails/Roads | Comments
Anticipated woodies | Various | High | High | High | High | monitor, eradicate*
Riparian invasive trees | Various | High |  |  |  | monitor, eradicate*
Arundo donax | giant reed, arundo | Medium |  |  |  | monitor, prevent
Centaurea calcitrapa | purple starthistle |  |  | High |  | monitor, prevent
Centaurea solstitialis | yellow starthistle |  |  | Low | High | monitoring, control
Eichhornia crassipes | water hyacinth |  | Medium |  |  | monitor, control
Foeniculum vulgare | fennel | Medium |  |  |  | monitor, control
Lepidium latifolium | perennial peppergrass | Medium | Medium |  |  | monitor, control*
Rubus armeniacus | Himalaya blackberry | Low |  |  | Low | monitor (previously known as Rubus discolor)
*Avoid management work when nesting birds in forests are easily disturbed.

## Table 2--Schedule
Weed Management Plan
Table 2. Management Implementation Schedule
Updated: 7/2001
Note: purple fields are calculated for you automatically
Codes: S=survey; T=treatment; P=plan control efforts
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4
Target Species | Win | Spr | Sum | Fall | Win | Spr | Sum | Fall | Win | Spr | Sum | Fall | Win | Spr | Sum | Fall
Anticipated woodies | P | ST |  | T | P |  |  |  | P |  |  |  | P
Riparian invasive trees | P | ST |  | ST | P |  |  |  | P |  |  |  | P
Arundo donax | P | S |  | T | P |  |  |  | P |  |  |  | P
Centaurea calcitrapa | P |  | ST |  | P |  |  |  | P |  |  |  | P
Centaurea solstitialis | P | T | ST |  | P |  |  |  | P |  |  |  | P
Eichhornia crassipes | P |  | ST | T | P |  |  |  | P |  |  |  | P
Foeniculum vulgare | P | S | S | T | P | ST | ST | ST | P |  |  |  | P
Lepidium latifolium | P: P; S: S; S: ST; P: P; P: P |  |  |  | P
Rubus armeniacus | [12 empty] | P | bar: P; S to P; P

## Table 3--Estimated costs
Weed Management Plan
Table 3. Estimated Resource Costs to Implement Weed Management Plan
Updated: 7/2001
Note: you must enter data in yellow fields, purple fields are calculated for you automatically.
|  |  | Year 1 | Year 2 | Year 3 | Year 4
Project/Target | Resource | Items/Comments: | Est: | Est: | Est: | Est: | 4-Year Est.
Anticipated woodies | Hrs-Staff/Interns: |  | 16 | 16 | 16 | 16 | 64
| Hrs-Volunteers: |  | 60 | 60 | 60 | 60 | 240
| $-Other Costs: | fuel, gear, herbicide, refreshments | 45 | 45 | 45 | 45 | 180
Riparian invasive trees | Hrs-Staff/Interns: |  | 232 | 162 | 113 | 79 | 586
| Hrs-Volunteers: |  | 900 | 630 | 441 | 309 | 2280
| $-Other Costs: | fuel, gear, herbicide, refreshments | 275 | 195 | 115 | 81 | 666
Arundo donax | Hrs-Staff/Interns: |  | 8 | 4 | 4 | 4 | 20
| Hrs-Volunteers: |  | 15 | 15 | 15 | 15 | 60
| $-Other Costs: | fuel, herbicide, refreshments | 25 | 25 | 25 | 25 | 100
Centaurea calcitrapa | Hrs-Staff/Interns: |  | 8 | 8 | 8 | 8 | 32
| Hrs-Volunteers: |  | 6 | 6 | 6 | 6 | 24
| $-Other Costs: | fuel, herbicide, refreshments | 35 | 35 | 35 | 35 | 140
Centaurea solstitialis | Hrs-Staff/Interns: |  | 16 | 16 | 16 | 16 | 64
| Hrs-Volunteers: |  | 60 | 60 | 60 | 60 | 240
| $-Other Costs: | contractors, refreshments | 45 | 45 | 45 | 45 | 180
Eichhornia crassipes | Hrs-Staff/Interns: |  | 24 | 24 | 24 | 24 | 96
| Hrs-Volunteers: |  | 220 | 220 | 220 | 220 | 880
| $-Other Costs: | equipment, materials, refreshments | 440 | 140 | 140 | 140 | 860
Foeniculum vulgare | Hrs-Staff/Interns: |  | 52 | 26 | 13 | 8 | 99
| Hrs-Volunteers: |  | 174 | 87 | 44 | 0 | 305
| $-Other Costs: | herbicides, materials, refreshments | 110 | 55 | 28 | 14 | 207
Lepidium latifolium | Hrs-Staff/Interns: |  | 80 | 48 | 48 | 48 | 224
| Hrs-Volunteers: |  | 100 | 100 | 100 | 100 | 400
| $-Other Costs: | fuel, gear, herbicide, mowing, contractors | 1500 | 1500 | 1500 | 1500 | 6000
Rubus armeniacus | Hrs-Staff/Interns: |  | 16 | 16 | 16 | 16 | 64
| Hrs-Volunteers: |  | 72 | 72 | 72 | 72 | 288
| $-Other Costs: | fuel, gear, herbicide, refreshments | 45 | 45 | 45 | 45 | 180
Grand Totals: | Hrs-Staff/Interns: |  | 452 | 320 | 258 | 219 | 1249
| Hrs-Volunteers: |  | 1607 | 1250 | 1018 | 842 | 4717
| $-Other Costs: |  | 2520 | 2085 | 1978 | 1930 | 8513

## Table 4--Actual Expenses
Weed Management Plan
Table 4. Itemized Actual Annual Cost and Labor Worksheet for Each Target Weed
Year: 2001
Note: you must enter data in yellow fields, purple fields are automatically calculated for you.
Target Weed/Project: |  | Anticipated woodies
Updated: 7/2001
Date | Item/Person | Staff Hrs | Vol. Hrs | Cost ($) | Notes
Jan. 1 | Monitoring | 8 | 12 | 10 | gas, refreshments
Apr. 1 | Weed Removal | 8 | 30 | 20 | gas, refreshments, herbicide, worktools
Aug. 4 | Weed Removal | 3 | 12 | 10 | gas, refreshments
Totals: |  | 19 | 54 | 40
Target Weed/Project: |  | Riparian invasive trees
Updated: 7/2001
Date | Item/Person | Staff Hrs | Vol. Hrs | Cost ($) | Notes
Totals:
Target Weed/Project: |  | Arundo donax
Updated: 7/2001
Date | Item/Person | Staff Hrs | Vol. Hrs | Cost ($) | Notes
Totals:
Target Weed/Project: |  | Centaurea calcitrapa
Updated: 7/2001
Date | Item/Person | Staff Hrs | Vol. Hrs | Cost ($) | Notes
Totals:
Target Weed/Project: |  | Centaurea solstitialis
Updated: 7/2001
Date | Item/Person | Staff Hrs | Vol. Hrs | Cost ($) | Notes
Totals:
Target Weed/Project: |  | Eichhornia crassipes
Updated: 7/2001
Date | Item/Person | Staff Hrs | Vol. Hrs | Cost ($) | Notes
Totals:
Target Weed/Project: |  | Foeniculum vulgare
Updated: 7/2001
Date | Item/Person | Staff Hrs | Vol. Hrs | Cost ($) | Notes
Totals:
Target Weed/Project: |  | Lepidium latifolium
Updated: 7/2001
Date | Item/Person | Staff Hrs | Vol. Hrs | Cost ($) | Notes
Totals:
Target Weed/Project: |  | Rubus armeniacus
Updated: 7/2001
Date | Item/Person | Staff Hrs | Vol. Hrs | Cost ($) | Notes
Totals:

## Table 5--Resource Summary
Weed Management Plan
Table 5. Projected and Actual Resource Uses (per year)
Year: 2001
Updated: 7/2001
Note: purple fields are calculated automatically
Differences
| Staff Hrs |  | Volunteer Hrs |  | Expenses |  | (Estimated - Actual)
Species/Common name | Est. | Actual | Est. | Actual | Est. | Actual | Staff Hrs | Vol. Hrs | Expenses
Anticipated woodies | 16 | 19 | 60 | 54 | 45 | 40 | -3 | 6 | 5
Riparian invasive trees | 232 |  | 900 |  | 275 |  | 232 | 900 | 275
Arundo donax | 8 |  | 15 |  | 25 |  | 8 | 15 | 25
Centaurea calcitrapa | 8 |  | 6 |  | 35 |  | 8 | 6 | 35
Centaurea solstitialis | 16 |  | 60 |  | 45 |  | 16 | 60 | 45
Eichhornia crassipes | 24 |  | 220 |  | 440 |  | 24 | 220 | 440
Foeniculum vulgare | 52 |  | 174 |  | 110 |  | 52 | 174 | 110
Lepidium latifolium | 80 |  | 100 |  | 1500 |  | 80 | 100 | 1500
Rubus armeniacus | 16 |  | 72 |  | 45 |  | 16 | 72 | 45
Resource Budget Summaries | 452 | 19 | 1607 | 54 | 2520 | 40 | 433 | 1553 | 2480